| Joint Collaborative Team on 3D Video Coding Extension Development of ITU-T SG 16 WP 3 and ISO/IEC JTC 1/SC 29/WG 11 6th Meeting: Geneva, CH, 25 Oct. – 1 Nov. 2013 | Document: JCT3V-F0001 |
| --- | --- |

| Title: | JCT-3V AHG Report: JCT-3V project management (AHG1) |  |  |
| --- | --- | --- | --- |
| Status: | AHG report input to JCT-3V |  |  |
| Purpose: | AHG report |  |  |
| Author(s) or Contact(s): | Gary J. Sullivan Microsoft Corp. 1 Microsoft Way Redmond, WA 98052 USA Jens-Rainer Ohm Institute of Communications Engineering RWTH Aachen University Melatener Straße 23 D-52074 Aachen | Tel: Email: Tel: Email: | +1 425 703 5308 garysull@microsoft.com +49 241 80 27671 ohm@ient.rwth-aachen.de |
| Source: | AHG |  |  |

_____________________________

# Abstract

This document reports on the work of the JCT-3V ad hoc group on Project Management, including an overall status report on the project and the progress made during the interim period since the last meeting.

# Mandates

At the fifth meeting of the ITU-T/ISO/IEC Joint Collaborative Team on 3D Video Coding Extension Development (JCT-VC), an ad hoc group on Project Management was established with the following mandates:

- Coordinate overall JCT-3V interim efforts

- Report on project status to JCT-3V reflector

- Provide report to next meeting on project coordination status

The reflector used for discussions by the JCT-3V and all of its AHGs is jct-3v@lists.rwth-aachen.de. For subscription to this list, see http://mailman.rwth-aachen.de/mailman/listinfo/jct-3v. The current number of subscribers on the reflector is 704.

- Activity

The work of the JCT-3V overall has proceeded well in the interim period. A large amount of discussion was carried out on the group email reflector. All documents from the preceding meeting had been made available at the document site (http://phenix.it-sudparis.eu/jct3v/) or the ITU-based JCT-3V site (http://wftp3.itu.int/av-arch/jct3v-site/2013_07_E_Vienna/), particularly including the following:

- The meeting report (JCT3V-E1000)

- the 7th version of specification Draft of the AVC 3D extension framework (3D-AVC, which had been issued as an ISO/IEC Study of DAM document) (JCT3V-E1002)

- the 7th test model of the AVC 3D extension framework (3D-AVC) (JCT3V-E1003)

- the 5th version of draft text of the Multiview HEVC extension (MV-HEVC) (which had been issued as an ISO/IEC DAM document) (JCT3V-E1004)
Note: Due to delays in issuing the DAM ballot (even though the document was submitted to ISO in time), the ballot only closes by 2014-01-16, which is only 1 day before the 7th JCT-3V meeting ends, such that a delay of FDAM by 1 meeting cycle appears unavoidable.

- the 5th test model of the HEVC 3D extension framework (3D-HEVC) (JCT3V-E1005)

- the 1st draft of HEVC 3D extension text specification (JCT3V-E1001)

- the 4th Draft of MVC plus depth conformance specification (which had been issued as an ISO/IEC Study of DAM document) (JCT3V-E1006)

- the 2nd Draft of MVC plus depth reference software specification (3D-AVC, which had been issued as an ISO/IEC Study of PDAM document) (JCT3V-E1010)

- the 2nd Draft of the AVC 3D conformance specification (JCT3V-E1009)

- the 2nd Test Model of MFC (JCTVC-E1008)

- the 1st draft of MFC conformance (which had been issued as an ISO/IEC PDAM document) (JCTVC-E1012)

- the 1st draft of MFC reference software (which had been issued as an ISO/IEC PDAM document) (JCTVC-E1013)

- the 3D Video Subjective Quality Assessment Test Plan  (JCTVC-E1011)

- Common Test Conditions of 3DV Core Experiments (JCT3V-E1100)

- Finalized core experiment descriptions (JCT3V-E1101 through JCT3V-E1105).

The 15 ad hoc groups and 5 core experiments had made progress, and various reports from those activities had been submitted.

The software for ATM version 9, and HTM version 8 had been prepared and released approximately as scheduled. Alignment of HTM (for both MV-HEVC and 3D-HEVC) with HM11/12 is finalized.

A "bug tracking" systems for software and text specifications had been installed for MV/3D HEVC software and text issues, and recently, an equivalent system was set up for 3D-AVC / ATM development (with special ticket lists for 3D ATM software, 3D-AVC text, MVC+D text and 3D-AVC test model). The sites are https://hevc.hhi.fraunhofer.de/trac/3d-hevc and https://hevc.hhi.fraunhofer.de/trac/3d-avc/. The bug tracker reports were automatically forwarded to the group email reflector, where the issues could be further discussed.

More than 240 input contributions to the current meeting had been registered. A significant number of late-registered and late-uploaded contributions were noted again.

The meeting announcement had been made available from the aforementioned document site and http://wftp3.itu.int/av-arch/jct3v-site/2013_10_F_Geneva/JCT3V-E_Logistics.doc. A joint meeting of AHG7 (high level syntax) with JCT-VC on topics of HEVC high-level syntax, two days prior to the current JCT-3V meeting, was also organized.

A preliminary basis for the document subject allocation and meeting notes had been circulated to the participants as http://wftp3.itu.int/av-arch/jct3v-site/2013_10_F_Geneva/JCT3V-F_Notes_d0.doc.