## Slide 1: MPEG-PCC AhG Dashboard
Period MPEG#126 – MPEG#127
Note: This document will be updated after each AhG call
Update AhG Call#23: 2019-06-27
Chairs: Ralf Schaefer, Khaled Mammou, Madhukar Budagavi

## Slide 2: Agenda Call#23
Welcome
Review of the agenda
Review of the status of the AhG mandates with emphasis on conduct the CEs/EEs/VEs and dissemination
AOB (short report on PCC/Systems meeting)

## Slide 3: Mandates of the AhG
Update the CTC and provide updated anchor points
Update the TMs (SW and documentation) during the editing period
Coordinate activities on the V-PCC Reference SW and G-PCC Reference SW
Conduct the PCC Core Experiments, Exploration Experiments and Validation Experiment
Finalize editing of V-PCC Study of CD and G-PCC CD
Solicit contributions on profiles and conformance for V-PCC
Solicit contributions on additional PCC use cases
Coordinate scientific and technical dissemination of PCC
Coordinate communications of PCC to fairs, exhibitions, workshops and prepare a public web-site with relevant information about PCC
Solicit additional data sets for all categories

## Slide 4: Update the CTC and provide updated anchor points
Common Test Conditions for PCC: w18474 published (WORD document and both templates)
V-PCC performance evaluation and anchor results: w18477 (10/05/2019). Sent to the reflector on 21/5/2019, but not yet uploaded
V-PCC Test Model: w18475 (03/05/2019)
G-PCC performance evaluation and anchor results: w18476 published
G-PCC Test Model: w18473 published

## Slide 5: Update the TMs – TMC2
SW releases:
  5.1: new HLS conform to CD document w18180 (15/04/2019)
  5.2: Remove arithmetic coding, some updates, some bug fixes (18/04/2019)
  6.0:
    Adoptions of MPEG#126
    Updated HLS conform to 2nd Study of CD N18479
    Anchors not yet finished, will be delivered by the end of the week
    Vlad mentions that the Tag for release 6.0 is missing. Tag is still on 5.2. The version will be tagged in the coming days
  6.1:
    Will be delivered before the next meeting, performance will be the same as 6.0, so 6.0 should be used for all experiments. V6.1 be submitted during the Gothenburg meeting
V-PCC Codec description (Vlad): w18487 (13/6/2019): Delivered to the container. The document is not in perfect shape, but no comments have been received so far. Deadline for comments is now July 3rd.

## Slide 6: Update the TMs – TMC13
SW releases:
  Versions 5.1 and 6.0-rc1 of tmc13 containing the normative adoptions made in Geneva has been tagged as release-v5.1 and release-v6.0-rc1 (17/4/2019). Version 6.0 should be used for all experiments
  Version 6.1 will integrate elements that have no effect or an insignificant effect on the CTC
G-PCC codec description (Toshiyasu) : w18486 (31/5/2019)
  First version is in the container. Email with deadline of July 3rd has been sent to the reflector

## Slide 7: Conduct the CEs – TMC2
CE 0.2 on content (Ohji): w18482
CE 2.12 on visual quality (Danillo): w18481
CE 2.15 on attributes coding support (Sebastian): w18484
CE 2.17 on Smoothing (Julien): w18496
CE 2.18 on patch packing (Danillo): w18499
CE 2.19 on V-PCC tiles (Arash): w18485
CE 2.20 occupancy map 2D filters (Kangying): w18491
CE 2.24 on High Level syntax (Vlad): w18497
CE 2.25 on PCM Points placement (Jungsun): w18507
CE 2.26 on Enhanced Occupancy Map (Joan): w18508

## Slide 8: Conduct the CEs – TMC2
CE 2.27 on Encoder speed up (Rajan): w18509
CE 2.28 on Designing Conformance Units and SEI message (Alexis): w18510
CE 2.29 on Delta D1 projection directions (Rajan): w18531
EE 2.1 on 3D motion estimation (Junsik Kim): w18493
EE 2.4 on homography representation of per patch transform (Danillo): w18511
EE 2.5 rendering optimization (Sebastian): w18512
EE 2.6 mesh coding with V-PCC (Madhukar): w18513
VE 2.1 on removing arithmetic encoder (Jungsun): w18514 (30/03/2019)

## Slide 9: CE 0.2 on content
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Topic | Type | Status
Sony | Ohji Nakagami |  | C | 
Samsung | Indranil Sinharoy Rajan Laxman Joshi Madhkuar Budagavi | Samsung dataset (Cat 2) | P | No activity
Fraunhofer HHI | Thomas Ebner | HHI dataset (Cat 2) | P | No activity
Technicolor | Ralf Schaefer | HHI dataset (Cat 2) | C | 
Blackberry | David Flynn | - | R | 
Nokia | Mika Pesonen | - | R | 

## Slide 10: CE 2.12 on visual quality
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Sony | Danillo Graziosi Alexandre Zaghetto | P | SW provided privately, cross-checks are on-going
ITRI/MTK | Yiting Tsai Shengpo Wang | P | SW provided to PCC GIT
Samsung | Hossein Najafzadeh Madhukar Budagavi | C | 

## Slide 11: CE 2.15 on attributes coding
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Nokia | Mika Pesonen | P | 
Apple | Khaled Mammou Jungsun Kim | C | 
Technicolor/InterDigital | Julien Ricard | C | 
Sony | Danillo Graziosi | C | Received SW from Nokia. Cross-checks are still ongoing
LGE | Sejin Oh | C | 
Samsung | Indranil Sinharoy, Madhukar Budagavi | C | 

## Slide 12: CE 2.17 on smoothing
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Technicolor/InterDigital | Julien Ricard Céline Guede Joan Llach | P, C | SW will be provided tomorrow
MediaTek ITRI | Ya-Hsuan Lee Jian-Liang Lin Yi-Ting Tsai | P, C | SW provided to PCC GIT
Tencent | Arash Vosoughi | P, C | SW provided to PCC GIT
Huawei | Kangying Cai | C | 
Sony | Satoru Kuma | C | 
Samsung | Hossein Najaf-Zadeh Madhukar Budagavi | C | 

## Slide 13: CE 2.18 on patch packing
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Sony | Danillo Graziosi Alexandre Zaghetto | P | SW provided privately
Huawei | Cai Kangying | C | 
Samsung | Indranil Sinharoy, Madhukar Budagavi | C | 

## Slide 14: CE 2.19 on tiles
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | 
Tencent | Arash Vosoughi Sehoon Yea | P | SW provided to PCC GIT
Hanyang U. | Euee S. Jang | C | 
ETRI | Gun Bang Eun-Young | Cancel | 
Samsung | Rajan Laxman Joshi Hossein Najaf-Zadeh | Cancel | 
Kyung Hee Univ. | Jiheon Im Junsik Kim Kyuheon Kim | Cancel | 
Apple | Alexis Michael Tourapis Jungsun Kim Khaled Mammou | C | 
Remark: A number of participants indicated a change of their participation in this CE

## Slide 15: CE 2.20 occupancy map 2D filters
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Huawei | Kangying CAI | P,C | 
Futurewei | Vladyslav Zakharchenko | P,C | 
Tencent | Arash Vosoughi Sehoon Yea | P,C | 
MediaTek | Jian-Liang Lin Ya-Hsuan Lee | P,C | SW delivered to the GIT
ITRI | Yi-Ting Tsai | P,C | SW delivered to the GIT
Samsung | Madhukar Budagavi Rajan Joshi Youngho Oh Hossein Najaf-Zadeh | P,C | Samsung has 2 deliverables: One of them has been delivered to the GIT, the other one is still missing
Technicolor/InterDigital | Joan Llach | C | 
Sony | Satoru Kuma | C | 
Apple | Jungsun Kim | C | 
Nokia | Sebastian Schwarz | C | 
SJTU | Yingzhan Xu | C | 

## Slide 16: CE 2.24 on high level syntax
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Apple | Alexis Tourapis Jungsun Kim | P, C | SW is planned to be delivered this week
Huawei | Kangying CAI | P, C | SW not yet delivered
Futurewei | Vladyslav Zakharchenko | P, C | SW not yet delivered
Sony | Danillo Graziosi | C | 
Samsung | Rajan Joshi | C | 

## Slide 17: CE 2.25 on PCM points placement
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Apple | Jungsun Kim | P, C | SW is planned to be delivered this week
Tencent | Arash Vosoughi | P, C | SW delivered. There is with integration into TM2 V6.0. Not sure if a patch can be delivered for V6.0
Samsung | Rajan Joshi Indranil Sinharoy | C | 

## Slide 18: CE 2.26 on enhanced occupancy map
2018/06/14 V-PCC CE Software and results are released to cross-checkers
2019/06/24 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Technicolor/InterDigital | Jean-Claude Chevet Céline Guede Joan Llach | P | SW has been delivered privately
Samsung | Rajan Laxman Joshi Indranil Sinharoy | C | 

## Slide 19: CE 2.27 on encoder speedup
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Samsung | Esmaeil Faramarzi Rajan Joshi | P | 
Sony | Ohji Nakagami Satoru Kuma | C | Received SW from Samsung and cross-check is in progress
Apple | Jungsun Kim Khaled Mammou Alexis Tourapis | C | 

## Slide 20: CE 2.28 on designing conformance unit and SEI messages
2019-03-29 MPEG #126 meeting ends.
2019-04-15 V-PCC: Expected date for release of finalized CE description and CTC.
2019-07-03 MPEG document upload deadline
2019-07-08 MPEG #127 meeting starts
Participant | Contact | Type | Status
Apple | Alexis M. Tourapis Jungsun Kim Khaled Mammou | P | There is no SW deliverable for this CE
Samsung | Joshi Rajan Laxman | P | 

## Slide 21: CE 2.29 on delta D1 projection directions
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Samsung | Youngho Oh Rajan Joshi | P, C | 
Nokia | Sebastian Schwarz | P, C | May only be cross-checker
Apple | Jungsun Kim Khaled Mammou Alexis Tourapis | C | No SW received so far

## Slide 22: EE 2.1 on 3D motion estimation
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
KHU | Kyuheon Kim Junsik Kim Jiheon Im | P/C | Nobody involved in the CE was present in the call

## Slide 23: EE 2.4 on homography representation of per patch transform
2018/06/19 V-PCC CE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Sony | Danillo Graziosi Alexandre Zaghetto | P | SW will be provided in the next days
Nokia | Lauri Ilola | C | 
Technicolor/InterDigital | Julien Richard | C | 
Samsung | Madhukar | C | 
Kyung Hee University | Jiheon Im | C | 

## Slide 24: EE 2.5 on rendering optimization
No timeline described
Participant | Contact | Type | Status
Nokia | Sebastian Schwarz | P | No update
Samsung | Indranil Sinharoy Rajan Joshi | P | No update

## Slide 25: EE 2.6 on Mesh coding with V-PCC (update CE description)
2018/06/19 V-PCC EE Software and results are released to cross-checkers
2019/06/26 V-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Samsung | Madhukar Budagavi Sungryeul Rhyu Rajan Joshi | P | No update
Apple | Khaled Mammou | C | 
Futurewei | Vladyslav Zakharchenko | C | 
Sony | Danillo.Graziosi | C | 
IMT | Chao Cao | C | 
Remark: Contrary to the CE description, there is only one proponent in the EE

## Slide 26: VE 2.1 on Removing Arithmetic Coder
2018/04/03 Feedback from cross-checkers to the proponents
2019/04/07 Report the final results to the 3DG/PCC AhG via email reflector
Participant | Contact | Type | Status
Apple | Jungsun Kim | P | Arithmetic Coder has already been removed
Huawei | Kangying Cai | C | 
Sony | Danillo Graziosi | C | 

## Slide 27: Conduct the CEs – TMC13
CE 13.2 on Point Cloud tile and slice-based coding (YitingS): w18480
CE 13.10 on entropy coding evaluation (David): w18483
CE 13.14 on fixed point implementation (David): w18488 (15/04/2019)
CE 13.15 on LOD generation (Ohji): w18489
CE 13.18 on RAHT AC prediction (David): w18503
CE 13.19 on LOD specific quantisation (Dean Han): w18504

## Slide 28: Conduct the CEs – TMC13
EE 13.1 on prediction strategies (Sehoon): w18490
EE 13.2 on inter-prediction for attributes coding (Sehoon): w18505
EE 13.3 on lossless RAHT (David): w18506
EE 13.4 on G-PCC performance evaluation (Vlad): w18520 10/05/2019
  w18520 is available in draft, but it needs further clean up before upload. Vlad agreed to make the clean up and pass the document to Christian for publication
  Futurewei will not continue to work on this EE, but Tencent and Blackberry will do so. EE report should state the more rigorous test methodology

## Slide 29: CE 13.2 on tile and slice-based coding
2019/05/27 G-PCC CE Software and results are released to cross-checkers
2019/06/26 G-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
PKUSZ | Yiting Shao | P,C | SW and results have been uploaded to the GIT
Blackberry | David Flynn | P,C | Cross-check is on going
Panasonic | Noritaka Iguchi | C | 
Sony | Danillo Graziosi | C | Provided cross-check results to Yiting. Cross-checks matched
Tencent | Sehoon Yea | C | 

## Slide 30: CE 13.10 on tile and slice based coding
2019/05/27 G-PCC CE Software and results are released to cross-checkers
2019/06/26 G-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Blackberry | David Flynn | P,C | Code has been uploaded to the GIT including initial results
Tencent | Sehoon Yea | C | 

## Slide 31: CE 13.14 division approximation in fixed-point calculations
2019/05/27 Distribution of CE software and results for verification
2019/06/26 CE verification feedback
Participant | Contact | Type | Status
Apple | Khaled Mammou | P | No progress so far
Hanyang University | Euee Jang | C | 
Sony | Alexandre Zaghetto Danillo Graziosi | C | 
Tencent | Sehoon Yea | C | 

## Slide 32: CE 13.15 on LoD generation for spatial scalability
2019/05/27 G-PCC CE Software and results are released to cross-checkers
2019/06/26 G-PCC Preliminary feedback from cross-checkers to proponents
Participant | Contact | Type | Status
Sony | Ohji Nakagami Satrou Kuma | P | SW has been uploaded to the GIT. LG and Hanyang completed the cross-check
Apple | Khaled Mammou | C | 
Hanyang University | Euee S. Jang | C | 
LG Electronics Inc. | Sejin Oh | C | 
Panasonic | Toshiyasu Sugio | C | 

## Slide 33: CE 13.18 upsampled transform domain prediction in RAHT
2019/05/27 Distribution of CE software and results for verification
2019/06/26 CE verification feedback
Participant | Contact | Type | Status
BlackBerry | David Flynn | P | SW including results have been delivered to the GIT
Panasonic | Toshiyasu Sugio | C | 
Sony | Danillo Graziosi | C | 
Tencent | Sehoon Yea | C | 

## Slide 34: CE 13.19 on attribute layer quantization control
2019/05/27 Deliver source code and results for cross check
2019/06/26 Report of preliminary cross check results
Participant | Contact | Type | Status
Panasonic | Dean | P | 
Sony | Ohji Nakagami | C | Nothing received so far

## Slide 35: EE 13.1 on Prediction Strategies for Attribute Coding (not reviewed)
2019/06/19 Distribution of EE SW and results for verification
2019/06/26 EE verification feedback from cross-checkers to the proponents
Participant | Contact | Type | Status
Tencent | Sehoon Yea | P | 
Panasonic | Toshiyasu Sugio | C | 
PKU (new) |  | C | 

## Slide 36: EE 13.2 on Inter-prediction for Attribute Coding (not reviewed)
2019/06/19 Distribution of EE SW and results for verification
2019/06/26 EE verification feedback from cross-checkers to the proponents
Participant | Contact | Type | Status
Tencent | Sehoon Yea | P | Code is delivered to the cross-checker
BlackBerry | David Flynn | C | 

## Slide 37: EE 13.3 lossless RAHT (not reviewed)
2019/05/27 Distribution of CE software and results for verification
2019/06/26 CE verification feedback
Participant | Contact | Type | Status
Blackberry | David Flynn | P | 
Panasonic | Toshiyasu Sugio | C | 
Sony | Ohji Nakagami | C | 
Tencent | Sehoon Yea | C | 

## Slide 38: EE 13.4 on G-PCC performance evaluation (not reviewed)
2019/06/19 Reference results and compression presets delivered to the cross-checkers
2019/06/26 Preliminary feedback from cross-checkers to the proponents
Participant | Contact | Type | Status
Huawei | Kangying CAI | P, C | 
Futurewei | Vladyslav Zakharchenko | P, C | 
Apple | Khaled Mammou Jungsun Kim | P, C | 
Blackberry | David Flynn | P, C | 
Tencent | Sehoon Yea | P, C | 
Sony | Danillo Graziosi | P, C | 
Unified Streaming | Rufael Mekuria | P, C | 
InterDigital | Dong Tian | P, C | 

## Slide 39: Finalize editing of V-PCC Study of CD and G-PCC CD
Editing group is: Khaled Mamou, Rajan Joshi, Joan Llach, Sebastian Schwarz, Ali Tabatabai, Ohji Nakagami, Vladyslav Zakharchenko and Alexis Tourapis
As the AhG chair, Ralf Schaefer organizes calls
Editing group had 2 Webex meetings so as to produce the 2nd Study of CD. w18479 published. This includes all agreed changes from MPEG#126, the new adoptions and it addresses some of the NB comments
Editing group will now focus on NB comments and editors comments (Draft DoC for ISO/IEC CD 23090-5 Video-based Point Cloud Compression w18502: 17/05/2019)

## Slide 40: Finalize editing of V-PCC Study of CD and G-PCC CD
Editing group is: Ohji Nakagami, Khaled Mamou, David Flynn, Toshiyasu Sugio and Vladyslav Zakharchenko
Ohji organizes calls
Editing group had 8 Webex meetings so far, next and final one is scheduled for next week

## Slide 41: Solicit contributions on profiles and conformance for V-PCC
There was a first Webex on May 16th with 6 participants. Sebastian shorty summarized the situation that there are two schools. The first one wants a base profile with a minimum set of tools, where the second one suggests to include more tools. Discussion is still ongoing
Related output documents are published:
  New ideas on establishing PCC profiles: w18494
  CE P.0 on profiles: w18495
  Working Draft 1.0 of V-PCC Profiles: w18519

## Slide 42: Solicit contributions on additional PCC use cases
Ralf reminded the group to work on input documents on use cases for the next meeting

## Slide 43: Coordinate scientific and technical dissemination of PCC
Samsung shared the participation in the following events:
  AIS/SMPTE conference mainly attended by content creators: https://www.smpte.org/sections/san-francisco/events/smpte-and-ais-present-entertainment-technology-2019?action
  The 2019 5G & Beyond Forum at Univ. California, San Diego: http://5g.ucsd.edu/content/agenda-2019

## Slide 44: Coordinate communications of PCC to fairs, exhibitions, workshops and prepare a public web-site with relevant information about PCC (1/3)
In order to reach wider dissemination of MPEG’s work on Point Cloud Compression it has been suggested over the reflector:
  Open the PCC GIT to the public
  Establish a public website related to MPEG-PCC where PCC related documents can be published by those who would like to do so

## Slide 45: Coordinate communications of PCC to fairs, exhibitions, workshops and prepare a public web-site with relevant information about PCC (2/3)
Ralf explained that the PCC AhG chairs received a number of written support statements from those who were in favor of making the GIT (both V-PCC and G-PCC) publicly available before MPEG#127. One company that was in favor suggested to do this after a discussion at MPEG#127. No opposition has been received.
After a discussion, the AhG decided unanimously to make the GIT immediately public available. David Flynn will put this in action through setting up a mirror on the MPEG GitHub account at https://github.com/MPEGGroup. We would mirror the master branches and release tags of the tmc13 and tmc2 repositories. The public repositories will not be used for integration work and will, in effect, be read-only mirrors. Further suggestions can be provided in form of input documents to the next MPEG meeting.

## Slide 46: Coordinate communications of PCC to fairs, exhibitions, workshops and prepare a public web-site with relevant information about PCC (3/3)
Further Ralf informed the group that there were also support statements for making PCC documents publicly available. He explained that the idea is not to open the MPEG document repository, but to have another site where companies can make PCC documents available if they like to do so. Marius said that another application of the site is that conference papers could reference PCC documents that have been previously uploaded there. He pointed us to www.mpeg-pcc.org where he set up an initial version of the website. Documents can be uploaded by sending the documents to Marius or contributors can create their own account. Those who like can use this site immediately for making PCC documents public. Further suggestions can be provided in form of input documents to the next MPEG meeting.

## Slide 47: Solicit additional data sets for all categories
No input on this point

## Slide 48: AOB
Report on PCC/Systems meeting: Not covered as there was no time left