## Slide 1: MPEG-PCC AhG Dashboard
Period MPEG#127 – MPEG#128
Note: This document will be updated after each AhG call
Update AhG Call#28: 2019-10-03
Chairs: Ralf Schaefer, Khaled Mammou, Madhukar Budagavi

## Slide 2: Mandates of the AhG
Finalize editing of V-PCC DIS
Improve documentation material for G-PCC
Update the TMs (SW and documentation) during the editing period
Coordinate activities on the V-PCC Reference SW and G-PCC Reference SW
Update the CTC and provide updated anchor points
Conduct the PCC Core Experiments, Exploration Experiments and Validation Experiment
Solicit contributions on profiles and conformance for V-PCC
Solicit contributions on additional PCC use cases
Solicit contributions on SEI messages for V-PCC and G-PCC
Coordinate scientific and technical dissemination of PCC
Coordinate communications of PCC to fairs, exhibitions, workshops and enrich www.mpeg-pcc.org with relevant information about PCC
Solicit additional data sets for all categories

## Slide 3: Agenda Call#28
Welcome
Review of the agenda
Status of mandates of MPEG#127
AOB

## Slide 4: Update the CTC and provide updated anchor points
Common Test Conditions for PCC: w18665 (WORD document and both templates)
V-PCC performance evaluation and anchor results: w18668 published
V-PCC Test Model: w18666 published
G-PCC performance evaluation and anchor results: w18667
G-PCC Test Model: w18664

## Slide 5: Update the TMs – TMC2
SW releases:
  V7.0 has been submitted to the master branch on August 7th
  There is agreement that CTC must use HM-16.20+SCM-8.8. In future, once available, HM-16.21+SCM-8.8 can be used
V-PCC Codec description (Vlad): w18674 published

## Slide 6: Update the TMs – TMC13
SW releases:
  V7.0-rc1 has been released on August 14th
  V7.0 has been tagged on August 28th. There are no significant changes between the rc and the tagged version
  There will be a 7.1 update and it will contain some non-CTC related adoptions. There should be no change in performance (there may be a 1 byte difference in the header though, since it will add a field to the SPS/GPS. Blackberry crosschecked 7.0 and rc-7.0 and the results are the same.
G-PCC codec description (Toshiyasu) : w18673 published

## Slide 7: Conduct the CEs – TMC2
CE 2.12 on visual quality (Ya-Hsuan Lee): w18671
CE 2.17 on Smoothing (Julien): w18677
CE 0.2 on content (Ohji): w18672
EE 2.4 on homography representation of per patch transform (Danillo): w18683
EE 2.6 mesh coding with V-PCC (Madhukar): w18684
VE 2.2 Simplified color smoothing (Rajan): w18719
VE 2.3 Single pass boundary identification (Rajan): w18720
VE 2.4 on Attributes Coding (SebastianS): w18721

## Slide 8: Conduct the CEs – TMC13
CE 13.15 on LOD generation (Satoru Kuma): w18675
EE 13.2 on inter-prediction for attributes coding (Sehoon): w18680
EE 13.3 on lossless Lifting Scheme (David): w18681
CE 13.20 on Neighbors Weight Modification on G-PCC Lifting and Predicting scheme (YitingS): w18695
CE 13.21 on RAHT quantization (Danillo): w18696
CE 13.22 on Improvements to octree coding (SebastienL): w18712
CE 13.23 on Duplicated Points (SebastienL): w18713
CE 13.24 on Color Space (Sehoon): w18714

## Slide 9: Conduct the CEs – TMC13
EE 13.5 on Region-wise Quantization Control on Attribute Coding (Dean Han): w18715
EE 13.6 Geometry Quantization (Sehoon): w18716
EE 13.7 Interchannel prediction for near lossless coding (Sehoon): w18717
EE 13.13 on Lossless extention to RAHT (Toshiyasu): w18740
VE 13.1 Improved color transfer (Arash): w18718

## Slide 10: CE 2.12 on visual quality
Participant | Contact | Type | Status
MediaTek & ITRI | Jian-Liang Lin Ya-Hsuan Lee Yi-Ting Tsai | P | SW and results have been delivered
Sony | Danillo Graziosi | C | Cross-checkers provided results
2019/09/18 CE Software and results are released to cross-checkers
2019/09/25 Preliminary feedback from cross-checkers to proponents

## Slide 11: CE 2.17 on Smoothing
Participant | Contact | Type | Status
InterDigital | Julien Ricard Céline Guede | P, C | SW and results have been delivered
Sony | Ohji Nakagami Satoru Kuma | P, C | Sony did not receive SW/results, although that Julien sent the information per email. The emails may be blocked by a spam filter. Julien to sent SW/results again to Sony. Sony will try their best to have cross-checks ready before the AhG F2F
Samsung | Hossein Najaf-Zadeh Rajan Laxman Joshi Madhukar Budagavi | C | 
Nokia | Sebastian Schwarz | C | Chross-check provided for 32 frames
2019/09/20 Code base and results delivered to cross-checkers (32 and ALL frames)
2019/09/27 Preliminary feedback from cross-checkers to proponents

## Slide 12: CE 0.2 on content
Participant | Contact | topic | Type | Status
Sony | Ohji Nakagami |  | C | Report uploaded. There was no activity
Samsung | Indranil Sinharoy Rajan Laxman Joshi Madhkuar Budagavi | Samsung dataset (Cat 2) | P | 
Fraunhofer HHI | Thomas Ebner | HHI dataset (Cat 2) | P | 
InterDIgital | Ralf Schaefer | HHI dataset (Cat 2) | C | 

## Slide 13: EE 2.4 on homography representation of per patch transform
Participant | Contact | Type | Status
Sony | Danillo Graziosi Alexandre Zaghetto | P | SW not yet shared. There are a lot of results to present. If members are interested, then SW can be shared later
Nokia | Lauri Ilola | C | 
ITRI | Yiting Tsai | C | 
2019-09-18 V-PCC CE Software and results are released to cross-checkers
2019-09-25 V-PCC preliminary feedback from cross-checkers

## Slide 14: EE 2.6 mesh coding with V-PCC
Participant | Contact | Status | Type
Samsung | Madhukar Budagavi Sungryeul Rhyu Rajan Joshi | Report will be released tomorrow | Participant
Apple | Khaled Mammou |  | Participant
Sony | Danillo.Graziosi |  | Participant
IMT | Chao Cao |  | Participant
2019-09-18 V-PCC CE Software and results are released to cross-checkers
2019-09-25 V-PCC preliminary feedback from cross-checkers

## Slide 15: VE 2.2 Simplified color smoothing
Participant | Contact | Status | Type | 
Samsung | Rajan Joshi Hossein Najaf-Zadeh | The full-frame results were reported, cross-checked, the results announced on the reflector. It has been integrated in TMC2 v7.0. | P | 
Sony | Satoru Kuma |  | C | 
Tencent | Sehoon Yea |  | C | 
2019/07/12 Patch available in the uploaded document [1].
2019/07/19 Share full-frame results with the cross checkers
2019/07/29 Confirmation of the full-frame results by the cross checkers
2019/07/31 Integration of the method into the integration branch for TMC2 v7.0 (subject to confirmation from the cross checkers)
2019/07/31 Release of the results to the 3DG/PCC AhG via its email reflector
2019/09/30 Integration of the method into the VPCC text specification

## Slide 16: VE 2.3 Single pass boundary identification
Participant | Contact | Status | Type | 
Samsung | Rajan Joshi Hossein Najaf-Zadeh | The full-frame results were reported, cross-checked, the results announced on the reflector. It has been integrated in TMC2 v7.0. | P | 
Sony | Satoru Kuma |  | C | 
2019/07/12 Patch available in the uploaded document
2019/07/19 Share full-frame results with the cross checkers
2019/07/29 Confirmation of the full-frame results by the cross checkers
2019/07/31 Integration of the method into the integration branch for TMC2 v7.0
2019/07/31 Release of the results to the 3DG/PCC AhG via its email reflector
2019/09/30 Integration of the method into the VPCC text specification

## Slide 17: VE 2.4 on Attributes Coding
Participant | Contact | Status | Type | 
Nokia | Deepa Naik | SW has been released first time for TMC2 V6. Now SW has been released for TMV2 V7 and Sony is running the cross checks. Results from Nokia are still missing | P | 
Sony | Danillo Graziosi | Cross-checks for V6 have been provided | C | 
2019/09/05 Patch available in the uploaded document
2019/09/09 Share full-frame results with the cross checkers
2019/09/23 Confirmation of the full-frame results by the cross checkers
2019/09/30 Integration of the method into the integration branch for TMC2 v7.0

## Slide 18: CE 13.15 on LOD generation
Participant | Contact | Status | Type
Sony | Ohji Nakagami Satrou Kuma | SW and results have been delivered. Report has been already uploaded | P
Apple | Khaled Mammou |  | C
Hanyang University | Euee S. Jang |  | C
LG Electronics Inc. | Sejin Oh Hyejung Hur | Cross-checks are done and report has been uploaded | C
Panasonic | Toshiyasu Sugio | Cross-checks are done and report has been uploaded | C
2019-09-18: CE Software and results are released to cross-checkers
2019-09-25: Preliminary feedback from cross-checkers to proponents

## Slide 19: EE 13.2 on inter-prediction for attributes coding
Name | Company | Status | Type
Sehoon Yea | Tencent | Work ongoing | Proponent
David Flynn | Apple | No information | Crosscheck
2019-09-17: Deliver source code and results for cross check
2019-09-24: Report of preliminary cross check results

## Slide 20: EE 13.3 on lossless Lifting Scheme
Name | Company | Status | Type
Sehoon Yea | Tencent | SW provided | Proponent
Khaled Mammou | Apple | No information | Crosscheck
2019-09-10 [TMC13v7 + 4 weeks]: Deliver source code and results for cross check;
2019-09-24: [TMC13v7 + 6 weeks] Report of preliminary cross check results

## Slide 21: CE 13.20 on Neighbors Weight Modification on G-PCC Lifting and Predicting scheme
Participant | Contact | Status | Type
PKUSZ | Yiting Shao Qi Zhang | SW and results delivered | P
LG Electronics | Sejin Oh Hyejung Hur | Cross-checks are done and report has been uploaded | C
Xidian University | Wei Zhang |  | C
2019-09-02 [TMC13v7 + 3 weeks]: G-PCC CE Software and results are released to cross-checkers;
2019-09-16 [TMC13v7 + 5 weeks]: Preliminary CE feedback from cross-checkers to proponents;

## Slide 22: CE 13.21 on RAHT quantization
Participant | Contact | Status | Type
Sony | Alexandre Zaghetto Ali Tabatabai Danillo Graziosi | SW and results delivered | P
PKU | Yiting Shao | Cross checks are done | C
2019-09-18 CE Software and results are released to cross-checkers.
2019-09-25 Preliminary feedback from cross-checkers

## Slide 23: CE 13.22 on Improvements to octree coding
Name | Company | Status | Type
Sébastien Lasserre | BlackBerry | SW and results delivered. Combination with Tencent has been explored and combined SW has been provided | Proponent m48906
Xiang Zhang Wen Gao | Tencent | SW and results delivered Cross-checks delivered | Proponent m49231
Kahled Mammou | Apple |  | Crosschecker m48906
Sejin Oh Hyejung Hur | LG | Cross-checked both SW separately, not the combined one | Crosschecker m49231 m48906
Yiting | PKUSZ (added) | Cross-checking combined SW | 
 | Panasonic (added) | Cross-checking combined SW | 
Ziwei Wei | Tsinghua University |  | Crosschecker m49231
2019-09-02 [TMC13v7 + 3 weeks]: Deliver source code and results for cross check;
2019-09-16: [TMC13v7 + 5 weeks] Report of preliminary cross check results

## Slide 24: CE 13.23 on Duplicated Points
Name | Company | Status | Type
Sebastien Lasserre | BlackBerry | SW and results delivered | Proponent
David Flynn | Apple | Cross-check done | Crosschecker
2019-09-02 [TMC13v7 + 3 weeks]: Deliver source code and results for cross check;
2019-09-16: [TMC13v7 + 5 weeks] Report of preliminary cross check results

## Slide 25: CE 13.24 on Color Space
Name | Company | Status | Type
Sehoon Yea | Tencent | SW delivered | Proponent
David Flynn | Apple | No information | Crosscheck
2019-09-02 [TMC13v7 + 3 weeks]: Deliver source code and results for cross check;
2019-09-16: [TMC13v7 + 5 weeks] Report of preliminary cross check results;

## Slide 26: EE 13.5 on Region-wise Quantization Control on Attribute Coding
Participant | Contact | Status | Type
Panasonic | Dean | SW and results delivered | P
Apple | Khaled |  | P
Sony | Satoru Kuma | Cross-check is on-going | C
2019/09/18 Distribution of EE SW and results for verification
2019/09/25 EE verification feedback from cross-checkers to the proponents

## Slide 27: EE 13.6 Geometry Quantization
Participant | Contact | Status | Type
Tencent | Wen Gao | No information | P
PKUSZ | Yiting Shao | No information | C
Apple | Khaled Mammou | No information | 
2019/09/18 Distribution of EE SW and results for verification
2019/09/25 EE verification feedback from cross-checkers to the proponents

## Slide 28: EE 13.7 Interchannel prediction for near lossless coding
Name | Company | Status | Type
Sehoon Yea | Tencent | SW provided | Proponent
Khaled Mammou | Apple | No information | Crosscheck
2019-09-10 [TMC13v7 + 4 weeks]: Deliver source code and results for cross check;
2019-09-24: [TMC13v7 + 6 weeks] Report of preliminary cross check results;

## Slide 29: EE 13.13 on Lossless extention to RAHT
Name | Company | Status | Type
Toshiyasu Sugio | Panasonic | SW and results have been delivered | Proponent
Sebastien Lasserre | BlackBerry | Cross-check done | Crosscheck
Khaled Mammou | Apple |  | Crosscheck
Ohji Nakagami | Sony | Cross-check done | Crosscheck
2019-09-18: Deliver source code and results for cross check
2019-09-25: Report of preliminary cross check results

## Slide 30: VE 13.1 Improved color transfer
Participant | Contact | Status | Type | 
Tencent | Arash Vosoughi | No information | P | 
Apple | David Flynn | No information | C | 
2019/07/31 | Code base and results delivered to the cross-checkers available at http://mpegx.int-evry.fr/software/MPEG/PCC/CE/mpeg-pcc-tmc13/tree/mpeg127/ve13.1/recolour-20190722
2019/08/31 | Report the final results to the 3DG/PCC AhG via email reflector

## Slide 31: Finalize editing of V-PCC DIS
Editing group is: Khaled Mammou, Rajan Joshi, Pierre Andrivon, Sebastian Schwarz, Ali Tabatabai, Ohji Nakagami, Vladyslav Zakharchenko and Alexis Tourapis
As the AhG chair, Ralf Schaefer organizes calls
Editing group had 2 Webex meetings. AhG F2F meeting in Munich was devoted to progress work on DIS text. A separate report is available (m51183)
Editing Work is now in final stage. Ralf will try to set up another call of the V-PCC editors group before the start of MPEG#128
Text of ISO/IEC DIS 23090-5 V-PCC w18670 (2019/09/30)
DoC for ISO/IEC CD 23090-5 V-PCC published w18679

## Slide 32: Improve documentation material for G-PCC
Editing group is: Ohji Nakagami, Khaled Mammou, David Flynn, Toshiyasu Sugio and Vladyslav Zakharchenko
Ohji organizes calls
G-PCC Improvements (Ohji): w18669 published
Ohji-san reports that the plan is to move to DIS for G-PCC at the Geneva meeting. A F2F on Saturday after the MPEG meeting is in preparation

## Slide 33: Solicit contributions on profiles and conformance for V-PCC
Sebastian organized 2 online meetings. Latest update has been circulated. Outcome has been discussed during the Munich F2F meeting and is now integrated in DIS draft text.

## Slide 34: Coordinate communications of PCC to fairs, exhibitions, workshops and prepare a public web-site with relevant information about PCC
Nokia demonstrated V-PCC at IBC at their booth in the Future Zone 8.F46
InterDigital demonstrated V-PCC at IBC at their booth 14.B38
InterDigital demonstrated V-PCC to DVB CM-AVC group
Marius: Please check if there is any material (e.g. video) that could be made available and published on the open PCC website

## Slide 35: Coordinate activities on the V-PCC Reference SW and G-PCC Reference SW
Questions:
  What is the difference between the reference SW and the final version of the test model SW ?
  What else is needed ?
  Timeline compared to spec release ?
  Do we want a new parts ?
Discussion:
  Typically the reference SW is just a snapshot of a version of the test model code. There is nothing special to do particularly. There would be a document with one line of text and an attachment containing version X of the software. The TMs must be compliant with the standard text. We would probably wish to be doing a round of verification with test bitstreams too

## Slide 36: Solicit contributions on SEI messages for V-PCC and G-PCC
No update

## Slide 37: Coordinate scientific and technical dissemination of PCC
Nokia Technologies won IBC 2019 Best Conference Paper award. The paper will be available on the IBC website after the event

## Slide 38: Solicit contributions on additional PCC use cases
No update

## Slide 39: Solicit additional data sets for all categories
HHI and 4DViews were present at IBC and they may be able to provide additional category 2 datasets in future. Ralf will follow up

## Slide 40: AOB
We agreed to start the AhG meeting with V-PCC on Sunday at 9:00 in ITU room C2. After V-PCC we continue with G-PCC